## Dashboard
Executive Delivery Dashboard | [6 empty] | DELIVERY CON CHARLY BRITO
Demo Project · Platform migration · Demo Client · Cut-off: 02/10/2026 · Week 6 of 12 · [Your name]
ACTUAL PROGRESS |  | SPI · SCHEDULE | CPI · COST | ACCEPTANCE |  | OPEN RISKS |  | OVERALL STATUS
41% |  | 0.91111 | 0.984 | 60% |  | 5 |  | Off track
Plan 45% · -4 pts |  | EV / PV · 1.00 = on plan | EV US$984k · AC US$1,000k | 3 of 5 delivered · 1 overdue |  | 2 critical · 1 missing 4 fields
● On track |  | ● At risk | ● On track | ● Off track |  | ● Off track |  | 2 off track · 1 at risk
Earned value · this week's reading
PV, EV and AC at cut-off; SPI(t) measures delay in time; verified progress applies the rule chosen in Settings.
PV · PLANNED TO DATE |  | EV · EARNED VALUE | AC · ACTUAL COST | SPI(t) · TIME |  | SCHEDULE GAP (PERIODS) |  | VERIFIED PROGRESS
US$1,080k |  | US$984k | US$1,000k | 0.93939 |  | -0.36364 |  | 40%
Value that should be done |  | Actual progress 41% × budget | Spent to date | ES / elapsed periods |  | ES 5.6 of 6 week(s) |  | Rule 50/50 · SPI 0.89
S-curve · cumulative progress |  |  |  | Cumulative cost
Plan vs. actual; the gap between the lines is the delay. |  |  |  | Plan (PV) vs. actual cost (AC), in USD (axis in thousands).
Client acceptance |  |  |  | Heat map of open risks
Deliverables by status. Delivered is not accepted. |  |  |  | Number of risks by probability and impact.
|  |  |  | Probability ↓ / Impact → | [5 empty] | Status | Deliverables
|  |  |  | 5 | 0 | 0 | 1 | 0 | 0 | Accepted | 3
|  |  |  | 4 | 0 | 0 | 0 | 1 | 0 | Returned | 1
|  |  |  | 3 | 0 | 0 | 1 | 0 | 0 | Pending | 1
|  |  |  | 2 | 0 | 0 | 1 | 1 | 0 | Not delivered | 3
|  |  |  | 1 | 0 | 0 | 0 | 0 | 0
[5 empty] | 1 | 2 | 3 | 4 | 5
■ Critical ■ High ■ Medium ■ Low (zones adjustable in Settings)
Weekly indices · SPI, SPI(t) and CPI
SPI measures value and tends to 1.00 at closing; SPI(t) measures time. 1.00 = on plan.
Priority risks
The 5 open risks with the highest severity.
ID | Description |  | Owner | Response plan |  |  | Severity | Level | 4 fields?
R-01 | Maintenance window not approved in time |  | Tech lead | Escalate to client management; book an alternate window |  |  | 16 | Critical | Yes
P-01 | Key user unavailable for testing |  | PM | Agree on a substitute with the sponsor |  |  | 15 | Critical | Yes
R-02 | Vendor licenses not delivered |  |  | Request temporary licenses |  |  | 9 | High | No
R-04 | Delay in purchasing additional storage |  | Procurement | Escalate to procurement leadership |  |  | 8 | High | Yes
R-03 | Turnover in the infrastructure team |  | PM | Document and assign a backup per role |  |  | 6 | Medium | Yes
Decisions required from leadership
The only thing you type on this sheet: what you need, from whom and by when.
Decision required |  |  | Owner | Due date | Impact if not decided
Approve an alternate maintenance window |  |  | Client management | 2026-10-09 | The migration slips 2 weeks and SPI drops below 0.90
© Carlos Alberto Ruiz Brito · 14/10/2026 · Delivery con Charly Brito · carlosruizbrito.com · License CC BY 4.0 (use and adapt with attribution)

## Read Me
How to use this dashboard
15 minutes a week · fictitious sample data: delete it and enter your project's data
Goal | Answer four questions every week, on one page: are we on schedule?, is the money enough?, is the client accepting what we deliver? and which risks could change the outcome?
1 · Settings | Once: project, currency, approved budget (BAC), thresholds and even the status-light and status texts. The whole workbook adjusts itself.
2 · Weekly tracking | At the start: the cumulative plan for every week (baseline). Every Friday: actual progress and actual cost for the closed week. The current week is detected automatically.
3 · Deliverables | Status of each deliverable: Not delivered, Pending (under review), Returned or Accepted, with the date it was sent for review.
4 · Risks | Each risk or issue with owner, review date, trigger and response plan. Probability and impact from 1 to 5.
5 · Dashboard | Calculates itself. Only type the decisions you need from leadership. Print or export to PDF on one landscape page.
Cells | Cream with blue text = input. White = formulas: do not edit them.
Indicators | PV = planned value to date. EV = % actual progress × total budget. AC = actual cost. SPI = EV/PV (measures value, not time). CPI = EV/AC (cost). 1.00 = on plan.
SPI(t) | Earned Schedule: ES = planned periods the work done is worth. SPI(t) = ES / elapsed periods; schedule gap = ES − elapsed periods. Use it especially in the final stretch, when SPI tends to 1.00.
Earned value rule | In Settings choose 0/100, 50/50 or % estimate. With the weights on the Deliverables sheet, the dashboard calculates verified progress and its SPI, to compare it with the progress you entered.
Status light | ● On track · ● At risk · ● Off track. Overall status takes the worst of the five indicators: a green dashboard with an open critical risk is not green.
License | CC BY 4.0: you may use, copy and adapt this template, even commercially, with attribution: Carlos Alberto Ruiz Brito · Delivery con Charly Brito · carlosruizbrito.com
Version | v1.1 EN · 14/10/2026 · English edition of v1.1 (SPI(t), schedule gap in time, earned value rule and weekly indices chart). Dates in DD/MM/YYYY format.
© Carlos Alberto Ruiz Brito · 14/10/2026 · Delivery con Charly Brito · carlosruizbrito.com · License CC BY 4.0 (use and adapt with attribution)

## Settings
Settings
Everything that makes the dashboard dynamic: project, currency, thresholds and texts. Cream cells = editable.
Parameter | Value | What it does
1 · Project |  |  | Currency | Symbol
Project | Demo Project · Platform migration | Name in the dashboard header (fictitious example) | MXN | $
Client / sponsor | Demo Client | Fictitious example | USD | US$
Report owner | [Your name] | Who signs the report | EUR | €
Period name | Week | Week, Sprint, Fortnight… Used in headers and texts | COP | COL$
|  |  | CLP | CLP$
2 · Currency and budget |  |  | PEN | S/
Currency | USD | Pick from the currency table (column F); you can add others | ARS | AR$
Symbol (automatic) | US$ | Taken from the currency table | BRL | R$
Total approved budget (BAC) | 2400000 | Earned value base: EV = % actual progress × BAC | GTQ | Q
Show amounts in | Thousands | Units, Thousands or Millions (dashboard and cards) | CAD | C$
Divisor (automatic) | 1000
Suffix (automatic) | k |  | Show | Divisor | Suffix
Earned value rule | 50/50 | 0/100: only accepted counts · 50/50: half at start, half at acceptance · % estimate: progress reported by the owner (Deliverables sheet) | Units | 1
3 · Status-light thresholds |  |  | Thousands | 1000 | k
Progress: at risk from (points behind) | 5% | Delay against the baseline that triggers an alert | Millions | 1000000 | M
Progress: off track from (points behind) | 10%
SPI / CPI: at risk below | 0.95 | 1.00 = on plan
SPI / CPI: off track below | 0.9
Acceptance: max days under review | 15 | After this period, the deliverable is escalated
Critical risk from severity | 15 | Severity = probability × impact (1–25)
High risk from severity | 8
Medium risk from severity | 4 | Below = low
4 · Status-light texts
Green status | On track | E.g. Green, OK, En línea · change the texts before entering data
Yellow status | At risk | E.g. Amber, Yellow
Red status | Off track | E.g. Red, Critical
5 · Deliverable statuses
Not yet delivered | Not delivered | Change the texts BEFORE entering data
Under client review | Pending
Returned with comments | Returned
Formally accepted | Accepted
6 · Risks
Type 1 | Risk | Has not happened yet
Type 2 | Issue | Has already happened
Open status | Open
Closed status | Closed
Level 1 | Critical | Severity ≥ critical threshold
Level 2 | High
Level 3 | Medium
Level 4 | Low
© Carlos Alberto Ruiz Brito · 14/10/2026 · Delivery con Charly Brito · carlosruizbrito.com · License CC BY 4.0 (use and adapt with attribution)

## Weekly Tracking
Weekly tracking
Enter the plan (all weeks) and actuals (closed weeks only). Earned value, SPI, CPI and SPI(t) are calculated automatically.
Week | Cut-off date | Planned progress (cum.) | Actual progress (cum.) | Planned cost PV (USD) | Actual cost AC (USD) | Earned value EV (USD) | SPI | CPI | Progress variance (pts) | Status | ES · earned schedule | SPI(t) | Schedule gap (periods) | SPI | SPI(t) | CPI
1 | 2026-08-28 | 3% | 3% | 72000 | 72000 | 72000 | 1 | 1 | 0% | ● On track | 1 | 1 | 0 | 1 | 1 | 1
2 | 2026-09-04 | 8% | 8% | 192000 | 195000 | 192000 | 1 | 0.98462 | 0% | ● On track | 2 | 1 | 0 | 1 | 1 | 0.98462
3 | 2026-09-11 | 15% | 14% | 360000 | 345000 | 336000 | 0.93333 | 0.97391 | -1% | ● At risk | 2.8571 | 0.95238 | -0.14286 | 0.93333 | 0.95238 | 0.97391
4 | 2026-09-18 | 24% | 22% | 576000 | 540000 | 528000 | 0.91667 | 0.97778 | -2% | ● At risk | 3.7778 | 0.94444 | -0.22222 | 0.91667 | 0.94444 | 0.97778
5 | 2026-09-25 | 34% | 31% | 816000 | 760000 | 744000 | 0.91176 | 0.97895 | -3% | ● At risk | 4.7 | 0.94 | -0.3 | 0.91176 | 0.94 | 0.97895
6 | 2026-10-02 | 45% | 41% | 1080000 | 1000000 | 984000 | 0.91111 | 0.984 | -4% | ● At risk | 5.6364 | 0.93939 | -0.36364 | 0.91111 | 0.93939 | 0.984
7 | 2026-10-09 | 56% |  | 1344000 | [9 empty] | #N/A | #N/A | #N/A
8 | 2026-10-16 | 67% |  | 1608000 | [9 empty] | #N/A | #N/A | #N/A
9 | 2026-10-23 | 77% |  | 1848000 | [9 empty] | #N/A | #N/A | #N/A
10 | 2026-10-30 | 86% |  | 2064000 | [9 empty] | #N/A | #N/A | #N/A
11 | 2026-11-06 | 94% |  | 2256000 | [9 empty] | #N/A | #N/A | #N/A
12 | 2026-11-13 | 100% |  | 2400000 | [9 empty] | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A
SPI = EV / PV (value) · CPI = EV / AC (cost) · ES = planned periods the work done is worth · SPI(t) = ES / elapsed periods (time) · Gap = ES − elapsed periods
© Carlos Alberto Ruiz Brito · 14/10/2026 · Delivery con Charly Brito · carlosruizbrito.com · License CC BY 4.0 (use and adapt with attribution)

## Deliverables
Deliverables and acceptance
Delivered is not accepted: each deliverable with its status, days under review and its contribution to earned value under the chosen rule.
ID | Deliverable | Owner | Committed date | Sent for review | Status | Acceptance date | Days under review | Delay vs. commitment | Comment | Weight (% of total) | Estimated progress | Contribution per rule
E-01 | Solution design | Architect | 2026-09-04 | 2026-09-03 | Accepted | 2026-09-08 |  | 0 | Signed sign-off | 5% | 100% | 5%
E-02 | Work plan and baseline | PM | 2026-09-04 | 2026-09-04 | Accepted | 2026-09-07 |  | 0 |  | 5% | 100% | 5%
E-03 | Inventory and dependencies | Tech lead | 2026-09-11 | 2026-09-14 | Accepted | 2026-09-18 |  | 3 | Delivered 3 days late | 10% | 100% | 10%
E-04 | Migration plan | Tech lead | 2026-09-25 | 2026-09-25 | Returned |  | 7 | 0 | 2 client comments | 10% | 100% | 5%
E-05 | Test environment | Infrastructure | 2026-09-11 | 2026-09-11 | Pending |  | 21 | 0 | No response from key user | 10% | 100% | 5%
E-06 | Recovery testing (DR) | Infrastructure | 2026-10-16 |  | Not delivered |  |  |  |  | 20% | 10% | 10%
E-07 | Rollback plan | Tech lead | 2026-10-23 |  | Not delivered |  |  |  |  | 15% | 0% | 0%
E-08 | Closure sign-off | PM | 2026-11-13 |  | Not delivered |  |  |  |  | 25% | 0% | 0%
[9 empty] | Totals | 100% |  | 40%
Weights must add up to 100%. The contribution depends on the earned value rule (Settings).
© Carlos Alberto Ruiz Brito · 14/10/2026 · Delivery con Charly Brito · carlosruizbrito.com · License CC BY 4.0 (use and adapt with attribution)

## Risks
Risks and issues
A risk is managed only if it has all 4 fields: owner, review date, trigger and response plan.
ID | Type | Description | Owner | Review date | Trigger | Response plan | Prob. (1-5) | Impact (1-5) | Severity | Level | Status | 4 fields? | Review overdue? | key
R-01 | Risk | Maintenance window not approved in time | Tech lead | 2026-10-09 | No approval 5 days before | Escalate to client management; book an alternate window | 4 | 4 | 16 | Critical | Open | Yes | No | 16.094
R-02 | Risk | Vendor licenses not delivered |  | 2026-09-30 | Licenses not received by 10/10 | Request temporary licenses | 3 | 3 | 9 | High | Open | No | Yes | 9.093
P-01 | Issue | Key user unavailable for testing | PM | 2026-10-05 | Materialized | Agree on a substitute with the sponsor | 5 | 3 | 15 | Critical | Open | Yes | No | 15.092
R-03 | Risk | Turnover in the infrastructure team | PM | 2026-10-14 | Notice of a team member leaving | Document and assign a backup per role | 2 | 3 | 6 | Medium | Open | Yes | No | 6.091
R-04 | Risk | Delay in purchasing additional storage | Procurement | 2026-10-20 | PO not released by 15/10 | Escalate to procurement leadership | 2 | 4 | 8 | High | Open | Yes | No | 8.09
R-05 | Risk | Scope change in reports | PM | 2026-09-20 | Formal client request | Change control | 2 | 2 | 4 | Medium | Closed | Yes |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
© Carlos Alberto Ruiz Brito · 14/10/2026 · Delivery con Charly Brito · carlosruizbrito.com · License CC BY 4.0 (use and adapt with attribution)